## Slide 1: Regional Cooperation Council 13th Meeting of the South East European Investment Committee June 19, 2013 Proposed methodology for SEE 2020

## Slide 2
Objectives of the project
Project organization
Deliverables
Challenges
Tasks and next steps
The Consultant

## Slide 3: OBJECTIVES OF THE PROJECT (ToR)
The SEE 2020 Strategy is a strategic document of the SEE countries and should be owned by them. It will be endorsed through a relevant intergovernmental process.
The consultancy service under the current project:
  provides input for the development of the SEE 2020 strategy document
  assists RCC with the development of a comprehensive drafting process

## Slide 4: PROJECT ORGANIZATION
Management structure
Team Leader
R. Dobrinsky
Pillar 1 leader
S. Richter
Pillar 5 leader
V. Gligorov
Pillar 2 leader
Ch. Hartmann
Pillar 3 leader
G. Hunya
Pillar 4 leader
H. Vidovic
Dimension experts
Free Trade Area:
S. Richter
Comp. Environment:
P. Havlik
Global economy:
O. Pindyuk
Dimension experts
Education & skills:
Ch. Hartmann
R&D & Innovation:
Ch. Hartmann
Digital society:
V. Breitfuss
Culture & creative:
V. Copic
Dimension experts
Competitiveness:
G. Hunya
Ressources. :
A. Kovacevic
Dimension experts
Employment:
H. Vidovic
Skills & education:
K. Korolkova
Health:
M. Hofmarcher
Dimension experts
Public services:
V. Gligorov
Anti corruption:
L. Barrett

## Slide 5: DIVISION OF RESPONSIBILITIES
Main responsibilities of wiiw team
Team Leader
Liaison with RCC
Overall coordination of drafting process
Concordance of methodology
Lead Component 1 (overall strategy document) implementation
Interviews with relevant stakeholders
Coordinate work on pillar reports
Quality control
Lead work on drafting SEE 2020 Strategy
Presentation of the report to stakeholders
Pillar leaders
Lead pillar implementation (Component 2 – pillar reports)
Ensure consistency and cohesion of pillar/dimension strategies
Liaison with RCC/Dimension coordinators
Establish links to EU accession process, other pillars, dimensions and measures
Lead work on pillar dimensions
Interviews with relevant stakeholders
Integration of dimensions chapters into Pillar reports
Lead work on drafting Pillar reports and condensed versions for Component 1
Dimension experts
Develop dimension outline
Review and analyze dimension
Draft dimension measures
Prepare dimension chapters as inputs to Pillar reports
Junior experts
Support Pillar experts
Support Dimension experts
Review of materials

## Slide 6: DRAFTING PROCESS
Team Leader
Pillar experts
Dimension experts
Agreed methodology,
Report templates,
briefing
Agreed report templates, materials produced, briefing
Draft dimension chapter
Draft pillar reports
Condensed pillar chapters
Draft zero Strategy
Feedback
Feedback
Final draft dimension chapter
Final draft pillar reports
Condensed pillar chapters
Final draft Strategy
Feedback
Feedback
Final dimension chapter
Final pillar reports
Condensed pillar chapters
Final Strategy
Regional Cooperation Council, Dimension coordinators, relevant stakeholders
Quality control
Quality control
Quality control
Phase C
Phase B
Phase A

## Slide 7: DELIVERABLES
Main deliverables:
Zero version of the Strategy document + adaptations
Draft final version of the Strategy document
Final version of the Strategy document
5 pillar reports (draft and final versions)
Process management:
has to ensure that a very broad and diversified group of experts will deliver of coherent set of documents

## Slide 8: MAIN CHALLENGES
Time pressure and lack of availability of key players during summer months
Different level of coordination between dimensions:
some dimension are based upon a well functioning and institutionalized cooperation process; in others, this process has yet to be established
Regional ownership of the project requires strong governance structure

## Slide 9: TASKS OF WIIW TEAM
Review of state of play
  Collection of reports & information that is available
  Review of documents; consult relevant experts
Ensure coherence and cohesion
  analysis and assessments
  objectives, measures and actions
  cross-cutting issues
Support with additional expertise
  provide rationale for strategy and actions
  strategic input about goals and instruments
  provide assessment if actions and measures are feasible and consistent with overall Strategy targets and possibly EU strategic objectives
Support drafting of overall strategy
Leading role in drafting pillar reports

## Slide 10: NEXT STEPS AND REVISED TIMELINE
Phase A (20 June -12 July)
  Work on dimension chapters
  Compilation of draft pillar reports
  Draft zero Strategy document
Phase B (15 July – 30 August)
  Draft final pillar reports
  Draft final version of the SEE 2020 Strategy document
Phase C (2 September – 31 September)
  Final version of the SEE 2020 Strategy document
  Presentation to the SEE 2020 Coordination Board
Ongoing consultations with RCC, Dimension Coordinators and other stakeholders

## Slide 11: THE VIENNA INSTITUTE OF INTERNATIONAL ECONOMIC STUDIES
Independent, non-profit research institute and international think tank
One of the principle centres for research on CESEE
With expertise in country and cross-country analysis and a focus on real economy issues (e.g. competitiveness, structural change, labour market developments, international economics, etc.)
Comparative studies for national and international clients (e.g. EC, OECD, World Bank, ILO, UNIDO)
Some references
  Economic policy advice – Croatia (2001-2009), Macedonia (2005-2006), Serbia (2002-2004)
  Establishing Directorate of Economic Planning in Bosnia and Herzegovina (2004-2008, 2013-2015)
  Cooperating with the Stability Pact for Southeast Europe from its inception
  Regional hub for SEE in Global Development Network (GDN)